## Sheet1
N | Name | Description | Duration | Precendence | Resource
1 | PA | beginning of project | 0 | - | -
2 | A1 | excavation (abument 1) | 4 | PA | excavator
3 | A2 | excavation (pillar 1) | 2 | PA | excavator
4 | A3 | excavation (pillar 2) | 2 | PA | excavator
5 | A4 | excavation (pillar 3) | 2 | PA | excavator
6 | A5 | excavation (pillar 4) | 2 | PA | excavator
7 | A6 | excavation (abument 2) | 5 | PA | excavator
8 | P1 | foundation piles 2 | 20 | A3 | pile-driver
9 | P2 | foundation piles 3 | 13 | A4 | pile-driver
10 | UE | erection of temporary housing | 10 | PA | -
11 | S1 | formwork (abutment 1) | 8 | A1 | carpentry
12 | S2 | formwork (pillar 1) | 4 | A2 | carpentry
13 | S3 | formwork (pillar 2) | 4 | P1 | carpentry
14 | S4 | formwork (pillar 3) | 4 | P2 | carpentry
15 | S5 | formwork (pillar 4) | 4 | A5 | carpentry
16 | S6 | formwork (abutment 2) | 10 | A6 | carpentry
17 | B1 | concrete foundation (abutment 1) | 1 | S1 | concrete-mixer
18 | B2 | concrete foundation (pillar 1) | 1 | S2 | concrete-mixer
19 | B3 | concrete foundation (pillar 2) | 1 | S3 | concrete-mixer
20 | B4 | concrete foundation (pillar 3) | 1 | S4 | concrete-mixer
21 | B5 | concrete foundation (pillar 4) | 1 | S5 | concrete-mixer
22 | B6 | concrete foundation (abutment 2) | 1 | S6 | concrete-mixer
23 | AB1 | concrete setting time (abutment 1) | 1 | B1 | -
24 | AB2 | concrete setting time (pillar 1) | 1 | B2 | -
25 | AB3 | concrete setting time (pillar 2) | 1 | B3 | -
26 | AB4 | concrete setting time (pillar 3) | 1 | B4 | -
27 | AB5 | concrete setting time (pillar 4) | 1 | B5 | -
28 | AB6 | concrete setting time (abutment 2) | 1 | B6 | -
29 | M1 | masonry work (abutment 1) | 16 | AB1 | bricklaying
30 | M2 | masonry work (pillar 1) | 8 | AB2 | bricklaying
31 | M3 | masonry work (pillar 2) | 8 | AB3 | bricklaying
32 | M4 | masonry work (pillar 3) | 8 | AB4 | bricklaying
33 | M5 | masonry work (pillar 4) | 8 | AB5 | bricklaying
34 | M6 | masonry work (abutment 2) | 20 | AB6 | bricklaying
35 | L | delivery of preformed bearers | 2 | - | crane
36 | T1 | positioning (preformed bearer 1) | 12 | M1, M2, L | crane
37 | T2 | positioning (preformed bearer 2) | 12 | M2, M3, L | crane
38 | T3 | positioning (preformed bearer 3) | 12 | M3, M4, L | crane
39 | T4 | positioning (preformed bearer 4 | 12 | M4, M5, L | crane
40 | T5 | positioning (preformed bearer 5) | 12 | M5, M6, L | crane
41 | UA | removal of the temporary housing | 10 | - | -
42 | V1 | filling 1 | 15 | T1 | caterpillar
43 | V2 | filling 2 | 10 | T5 | caterpillar
44 | K1 | point 1 of cost function | 0 | - | -
45 | K2 | point 2 of cost function | 0 | - | -
46 | PE | end of project | 0 | T2, T3, T4, V1, V2, UA | -